## To Do & In-Progress
S.No. | Points | Comment | Status | Efforts | Remarks | Person responsible | Start Date | End Date | Dependencies
8 | Rejection Communication PAN | Partially working (Only SMS are being sent, All emails not sending & Rejection communication to the Branch is not working) | Demo Done | 2 days |  | Surabhi | 2023-03-01 | 2023-03-02 | subject to details share by religare
9 | Rejection Communication TAN | It was not discussed earlier at the time of development | Demo Done | 2 days | Email templates to be provided by religare. Same as PAN rejection | Surabhi | 2023-03-05 | 2023-03-07 | subject to details share by religare
12 | MIS download from NSDL and Upload in System | Partially Available (Only for PAN & TAN rest are pending yet, eTDS are also provided) | Demo Done |  | 24G to be considered in this scope itself | Prasang | 2023-03-08 | 2023-03-10
16 | Set Limit check is not working to the Vendor user & the wrong ack are assigned, as per the process/logic only those cases should assign which are uploaded by branches pdf only having Digitization flag “N” but there are assigned stages are shown with multiple stages (Batch Generation, NSDL Confirmation, Quality Check & Rejection Resolution). |  | Work in Progress | 1 day |  | Prasang | 2023-03-03 | 2023-03-04
19 | Complete GST with e-Invoicing | Need all format and clarity on this | Work in Progress |  |  | Shripat | 2023-02-25 | 2023-02-28 | subject to details share by religare
20 | Warehouse process | (it is a part of DMS. If NSDL asks for any document, then that detail is stored at warehouse. LOT of 1000(new) and 500 (corrections) is prepared and shared to NSDL) 12-01-2023 NA As of now. It will be maintained in audit trail also.TBD with debox and Religare. | To do |  | Laser Fiche to be provided by religare to debox .. Clarified by akmal sir that religare will provide DMS | Shripat | 2023-03-11 | 2023-03-14 | subject to details share by religare
24 | Users should not be allowed to occupy the range until they mark as received with existing occupied receiving serial numbers. Currently the system is allowed to occupy the range again & again after refreshing the page. |  | Demo Done | 2 days |  | Prasang | 2023-02-24 | 2023-02-24
32 | HO Level reports |  | Work in Progress | 10 days | Branch/Commission Report-DONE Collection Report-DONE Daily Unbilled Report -WIP | Prasang | 2023-02-20 | 2023-02-23

## Ready for QA
S.No. | Points | Comment | Status | Efforts | Remarks | Person responsible | Start Date | End Date
1 | Partially Working (Count of Rejected PAN application is not available) |  | Ready for QA | 3 | Demo Done
2 | (Branch/Region/Vendor/Roles and Rights) | super admin is required. | Ready for QA |  | Demo Done
4 | Cancellation |  | Ready for QA | 2 | Demo Done
7 | NSDL Status marking with WISDA response of scan images uploaded |  | Ready for QA |  | Demo Done
14 | Data Entry 1 and/or Data 2 & Validation |  | Ready for QA |  | Demo Done few observation found. that need to discuss with asim sir.
23 | Tracking of the courier details in the "Courier List" menu is not maintained. It's removed from the list after moving on to the next stage. |  | Ready for QA | 2 | Demo Done
25 | 2-3 seconds are taking to get the receive number, however in existing software it's not taking more than 1 second. |  | Ready for QA | 2 | Demo Done
26 | Receive range is occupied without entering the numbers into the box of receive range. |  | Ready for QA | 2 | Demo Done
27 | Wrong receive range allocated by the system. User has occupied the range for 5 ack numbers; however the system is allocated with 6 numbers (113-118). |  | Ready for QA | 2 | Demo Done
28 | There is 2 Dashboard screen are showing in BACKHO user. |  | Ready for QA | 2 | Demo Done
29 | Branch data is showing on screen which need to dispatch mark while we login the back office it's showing & click on "Switch to Back office" & |  | Ready for QA | 2 | Demo Done
30 | Another one showing with warehouse dispatch date while we click on the Dashboard button. |  | Ready for QA |  | Demo Done
31 | Branch Level Reports

## Next Scope Tasks
S.No. | Module | Points | Comment | Status | Efforts | Remarks | Person responsible | Start Date | End Date
1 |  | Partially working (Direct rejection is not available) | (HO can reject at any stage)-Rejection is available after QC. Cancellation will be done by HO but ony at initial Stage | Next Scope
2 |  | Audit Point & fulfilment | On Hold (As discussed in previous meetings) | Next Scope |  | Out of scope- not to be considered.
3 |  | Re-verification Process | After nsdl confirmation, the application is rejected by itd, and then they have to reprocess the sent application to reverification process | Next Scope
4 |  | Sub Agent Management |  | Next Scope
5 |  | Franchise – Branch Mapping /Franchise – Vendor Mapping | Branch and vendor mapping is already there and franchise not there | Next Scope |  | TBD
6 |  | Count of available ack for Digitization should be shown at Vendor Dashboard | Requirement given on Issue Report of Vendor Module | Next Scope |  | To be checked in this scope.
17 |  | User-wise Report of Daily digitized/Pending of PAN/TAN applications is required for reconciliation. | Requirement given on Issue Report of Vendor Module | Next Scope
18 |  | Vendor Limit setting |  | Next Scope |  | To be checked if done.
21 |  | Payment Gateway Integration |  | Next Scope |  | Initiate from religare
22 |  | 24G/AIR/SFT MIS ,Billing, Commission |  | Next Scope

## Consolidated List of tasks
S.No. | Module | Points | Comment | Status | Efforts | Remarks | Person responsible | Start Date | End Date
1 |  | Partially Working (Count of Rejected PAN application is not available) |  | Ready for QA | 3
2 |  | (Branch/Region/Vendor/Roles and Rights) | super admin is required. | Ready for QA
3 |  | Partially working (Direct rejection is not available) | (HO can reject at any stage)-Rejection is available after QC. Cancellation will be done by HO but ony at initial Stage | Next Scope
4 |  | Cancellation |  | Ready for QA | 2 | To be presented in demo by prasang
5 |  | Audit Point & fulfilment | On Hold (As discussed in previous meetings) | Next Scope |  | Out of scope- not to be considered.
6 |  | Re-verification Process | After nsdl confirmation, the application is rejected by itd, and then they have to reprocess the sent application to reverification process | Next Scope
7 |  | NSDL Status marking with WISDA response of scan images uploaded |  | Ready for QA |  | To be presented in demo by prasang
8 |  | Rejection Communication PAN | Partially working (Only SMS are being sent, All emails not sending & Rejection communication to the Branch is not working) | Work in Progress | 2 days |  | Surabhi
9 |  | Rejection Communication TAN | It was not discussed earlier at the time of development | To do |  | Email templates to be provided by religare. Same as PAN rejection | Surabhi
10 |  | Sub Agent Management |  | Next Scope
11 |  | Franchise – Branch Mapping /Franchise – Vendor Mapping | Branch and vendor mapping is already there and franchise not there | Next Scope |  | TBD
12 |  | MIS download from NSDL and Upload in System | Partially Available (Only for PAN & TAN rest are pending yet, eTDS are also provided) | To do |  | 24G to be considered in this scope itself | Prasang
14 |  | Data Entry 1 and/or Data 2 & Validation |  | Ready for QA |  | To be presented in Demo by Prasang
15 |  | Count of available ack for Digitization should be shown at Vendor Dashboard | Requirement given on Issue Report of Vendor Module | Next Scope |  | To be checked in this scope.
16 |  | Set Limit check is not working to the Vendor user & the wrong ack are assigned, as per the process/logic only those cases should assign which are uploaded by branches pdf only having Digitization flag “N” but there are assigned stages are shown with multiple stages (Batch Generation, NSDL Confirmation, Quality Check & Rejection Resolution). |  | Work in Progress | 3 days | 1 day | Prasang
17 |  | User-wise Report of Daily digitized/Pending of PAN/TAN applications is required for reconciliation. | Requirement given on Issue Report of Vendor Module | Next Scope
18 |  | Vendor Limit setting |  | Next Scope |  | To be checked if done.
19 |  | Complete GST with e-Invoicing | Need all format and clarity on this | Work in Progress |  |  | Shripat
20 |  | Warehouse process | (it is a part of DMS. If NSDL asks for any document, then that detail is stored at warehouse. LOT of 1000(new) and 500 (corrections) is prepared and shared to NSDL) 12-01-2023 NA As of now. It will be maintained in audit trail also.TBD with debox and Religare. | To do |  | Laser Fiche to be provided by religare to debox .. Clarified by akmal sir that religare will provide DMS | Shripat
21 |  | Payment Gateway Integration |  | Next Scope |  | Initiate from religare
22 |  | 24G/AIR/SFT MIS ,Billing, Commission |  | Next Scope
23 |  | Tracking of the courier details in the "Courier List" menu is not maintained. It's removed from the list after moving on to the next stage. |  | Ready for QA | 2 | DONE Demo to be given
24 |  | Users should not be allowed to occupy the range until they mark as received with existing occupied receiving serial numbers. Currently the system is allowed to occupy the range again & again after refreshing the page. |  | Work in Progress | 2 days |  | Prasang
25 |  | 2-3 seconds are taking to get the receive number, however in existing software it's not taking more than 1 second. |  | Ready for QA | 2 | DONE
26 |  | Receive range is occupied without entering the numbers into the box of receive range. |  | Ready for QA | 2
27 |  | Wrong receive range allocated by the system. User has occupied the range for 5 ack numbers; however the system is allocated with 6 numbers (113-118). |  | Ready for QA | 2
28 |  | There is 2 Dashboard screen are showing in BACKHO user: |  | Ready for QA | 2
29 |  | Branch data is showing on screen which need to dispatch mark while we login the back office it's showing & click on "Switch to Back office" & |  | Ready for QA | 2
30 |  | Another one showing with warehouse dispatch date while we click on the Dashboard button. |  | Ready for QA
31 |  | Branch Level Reports |  | Ready for QA
32 |  | HO Level reports |  | Work in Progress | 10 days | Branch/Commission Report-DONE Collection Report-DONE Daily Unbilled Report -WIP | Prasang

## Debox Sheet (hidden)
Points | Comment | Status | Effort | Debox Comment(07/02/23)
Front-End
Partially Working (Count of Rejected PAN application is not available) |  | DONE | 3
(Branch/Region/Vendor/Roles and Rights) | super admin is required. | DONE
Partially working (Direct rejection is not available) | (HO can reject at any stage)-Rejection is available after QC. Cancellation will be done by HO but ony at initial Stage | Next Scope
Cancellation |  | DONE | 2 | To be presented in demo by prasang
Audit Point & fulfilment | On Hold (As discussed in previous meetings) | Next Scope |  | Out of scope- not to be considered.
Re-verification Process | After nsdl confirmation, the application is rejected by itd, and then they have to reprocess the sent application to reverification process | Next Scope
NSDL Status marking with WISDA response of scan images uploaded |  | DONE |  | To be presented in demo by prasang
Rejection Communication PAN | Partially working (Only SMS is sending, All emails not sending & Rejection communication to the Branch is not working) | Provided by Religare | 2
Rejection Communication TAN | It was not discussed earlier at the time of development | This scope |  | Email templates to be provided by religare
Sub Agent Management |  | Next Scope
Franchise – Branch Mapping /Franchise – Vendor Mapping | Branch and vendor mapping is already there and franchise not there | Next Scope |  | TBD
MIS download from NSDL and Upload in System | Partially Available (Only for PAN & TAN rest are pending yet, eTDS are also provided) | In scope |  | 24G to be considered in this scope itself
Download the Status of Application and upload in System
Data Entry 1 and/or Data 2 & Validation |  | DONE |  | To be presented in Demo by Prasang
Count of available ack for Digitization should be shown at Vendor Dashboard | Requirement given on Issue Report of Vendor Module | Next Scope |  | To be checked in this scope.
Set Limit check is not working to the Vendor user & the wrong ack are assigned, as per the process/logic only those cases should assign which are uploaded by branches pdf only having Digitization flag “N” but there are assigned stages are shown with multiple stages (Batch Generation, NSDL Confirmation, Quality Check & Rejection Resolution). |  | Work in Progress | 3 | 1 day
User-wise Report of Daily digitized/Pending of PAN/TAN applications is required for reconciliation. | Requirement given on Issue Report of Vendor Module | Next Scope
Vendor Limit setting |  | Next Scope |  | To be checked if done.
Back-End
Complete GST with e-Invoicing | Need all format and clarity on this | Work in Progress
Warehouse process | (it is a part of DMS. If NSDL asks for any document, then that detail is stored at warehouse. LOT of 1000(new) and 500 (corrections) is prepared and shared to NSDL) 12-01-2023 NA As of now. It will be maintained in audit trail also.TBD with debox and Religare. | Clarified by akmal sir that religare will provide DMS |  | Laser Fiche to be provided by religare to debox
Payment Gateway Integration |  | Next Scope |  | Initiate from religare
24G/AIR/SFT MIS ,Billing, Commission |  | Next Scope
Tracking of the courier details in the "Courier List" menu is not maintained. It's removed from the list after moving on to the next stage. |  | DONE | 2 | DONE Demo to be given
Users should not be allowed to occupy the range until they mark as received with existing occupied receiving serial numbers. Currently the system is allowed to occupy the range again & again after refreshing the page. |  | Work in Progress | 2
2-3 seconds are taking to get the receive number, however in existing software it's not taking more than 1 second. |  | DONE | 2 | DONE
Receive range is occupied without entering the numbers into the box of receive range. |  | DONE | 2
Wrong receive range allocated by the system. User has occupied the range for 5 ack numbers; however the system is allocated with 6 numbers (113-118). |  | DONE | 2
There is 2 Dashboard screen are showing in BACKHO user: |  | DONE | 2
Branch data is showing on screen which need to dispatch mark while we login the back office it's showing & click on "Switch to Back office" & |  | DONE | 2
Another one showing with warehouse dispatch date while we click on the Dashboard button. |  | DONE
Branch Level Reports |  | DONE
HO Level reports |  | Work in Progress | 10 | Branch/Commission Report-DONE Collection Report-DONE Daily Unbilled Report -WIP